## Sheet1
Scenario | Test Case name | Test Case Description | Tester | Status | Comments | Use Case(s) | Functional Requirement(s)
Scenario 3 Power | Test System On/Off | Test that the system can be turned on and off without exiting the simulation |  | Not started |  | Power Use Case | Turning the machine on and off does not affect the stored data
Scenario 3 Power | Test System Exit | Test that exit ends the simulation |  | Not started |  | Power Use Case | Exiting the simulatoion must end the run and clear the stored data
Scenario 1 Racer Start | Test Sensor Start | Test start a Racer by a triggered sensor |  | Not started |  | Start Racer Use Case | A racer can start via a sensor or manual trigger
Scenario 1 Racer Start | Test Manual Start | Test start a Racer by the manual triggering of the channel |  | Not started |  | Start Racer Use Case | A racer can start via a sensor or manual trigger
Scenario 2 Racer DNF | Test Racer DNF | Test a racers ability to fail |  | Not started |  | Stop Racer Use Case | A racer can fail to complete a racer
Scenario 2 Racer Fall Starts | Test Racer Flase Start | Test resetting a racer at the start |  | Not started |  | Stop Racer Use Case | A racer can flase start and need to be reset
Sprint 2 | Functional Tests
| testNewRacer | Test creation of a Racer and associated getters | Sam | Ran - Passed |  |  | Racers has a Bib number
| testSensor | Test adding a Sensor to a start trigger and one to a stop trigger. Test ability to toggle a Sensor on and off | Sam | Ran - Passed | Merged with previous tests startsensor and stopsensor |  | Associate a specific trigger to a sensor
| TestLane | Test Lane class functionality | Sam | Ran - Passed |  |  | Handle multiple Racers at once, DNF cases, SWAP cases,
| testRacerStartFinish | Test starting and stoping a Racer and associated getters | Sam | Ran - Passed | Merged with TestLane |  | Racer knows own time info
| testUpdateTime | Test ability to update time | Sam | Ran - Passed
| TestNormalIND | Test creation and sample run of an individual event | Sam | Ran - Passed
| TestNormalPARAIND | Test creation and sample run of a paraividual event | Sam | Ran - Passed
| TestNormalGRP | Test a group event |  | In progress
| TestNormalPARAGRP | Test a paragrpividual event |  | In progress